# AWS First Cloud AI Journey – Project Plan

# [Project team] – [Fpt University] – [Blood Donation Support System]

# [11/11/2025]

- Table of Contents

1	BACKGROUND and motivation	3

1.1	executive summary	3

1.2	PROJECT SUCCESS CRITERIA	3

1.3	Assumptions	3

2	SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM	3

2.1	Technical Architecture Diagram	3

2.2	Technical Plan	4

2.3	Project Plan	4

2.4	Security Considerations	4

3	Activities AND Deliverables	5

3.1	Activities and deliverables	5

3.2	OUT OF SCOPE	5

3.3	PATH TO PRODUCTION	5

4	EXPECTED AWS COST BREAKDOWN BY SERVICES	5

5	TEAM	6

6	resources & cost estimates	6

7	Acceptance	7

# BACKGROUND and motivation

## executive summary

The Blood Donation Support System (BDSS) is a cloud-based platform designed to connect blood donors with medical facilities efficiently and reliably. The system addresses limitations in manual donor management, slow matching processes, and fragmented data storage.

BDSS uses a scalable and secure architecture deployed on AWS Cloud, leveraging services such as Route 53, CloudFront, API Gateway, Amazon EC2, RDS MySQL, Cognito, and a complete CI/CD workflow via GitLab → CodePipeline → CodeBuild.
The solution provides four user roles (Guest, Member, Staff, Admin), enabling blood donation registration, donor search, blood inventory management, emergency notifications, and reporting dashboards.

## PROJECT SUCCESS CRITERIA

- Reduce 60–70% of response time in finding suitable donors (by blood type and location).

- Achieve >99% system uptime using AWS managed services.

- Ensure secure access through Cognito and IAM with zero unauthorized access incidents.

- Complete CI/CD pipeline enabling deployments in <5 minutes, with automated builds and testing.

- Maintain stable performance for up to 5,000 monthly users with auto scaling.

- Ensure database consistency with RDS automated backups, point-in-time recovery, and encrypted storage.

## Assumptions

- The customer will provide accurate business workflows related to blood donation processes.

- GitLab repository and credentials will be accessible for CI/CD integration.

- All workloads will operate within one AWS Region.

- No on-premise system integration required during the initial phase.

- Frontend code supports static hosting via S3 + CloudFront.

- The project will not include Machine Learning or AI modules in this phase.

- Traffic is expected to remain within free-tier limits for most services.

# SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM

## Technical Architecture Diagram

Dựa theo hình kiến trúc bạn gửi, hệ thống gồm các lớp:

- Edge Networking

- Route 53: DNS & domain hosting

- CloudFront: CDN + caching static assets

- AWS WAF: Web application firewall

- Application Layer

- Frontend hosted on S3 + CloudFront

- Backend on Amazon EC2 Auto Scaling Group

- API Gateway làm entry point cho API

- RDS MySQL lưu dữ liệu máu, thông tin người hiến, lịch sử hiến

- Networking

- VPC 10.0.0.0/16

- Public subnet: NAT Gateway

- Private subnet: EC2 + RDS

- Internet Gateway for external access

- CI/CD Layer

- GitLab → CodePipeline → CodeBuild → EC2 Deployment

- CloudFormation quản lý hạ tầng IaC

- Monitoring & Security Layer

- Cognito (AuthN & AuthZ for 4 roles)

- IAM, Secrets Manager, CloudWatch, CloudTrail

- SNS for alerting

## Technical Plan

The partner will implement the architecture using IaC (CloudFormation) to ensure consistent and reproducible deployments.
CI/CD pipeline will automatically build, test, and deploy code upon GitLab commits.

Additional configuration:

- WAF rules approval from the customer

- IAM roles restricted following least-privilege model

- System logs and alarms configured under CloudWatch

Test cases (Appendix) include:

- Authentication flows

- API integration

- Database failover

- Load testing scenario

## Project Plan

Agile Scrum framework across 8 sprints, each 2 weeks.
Stakeholders (Admin, IT Lead, Project Supervisor) join sprint reviews & retrospectives.

Team responsibilities:

- Developer: build frontend, backend, integrate AWS

- Cloud Engineer: create infrastructure, networking, CI/CD

- QA: functional & security testing

Communication cadence:

- Weekly meeting

- Daily Slack/Teams updates

- Monthly technical report

Knowledge transfer sessions at end of project.

## Security Considerations

Access:

- Cognito user pool + MFA (optional)

- IAM roles with least privilege

Infrastructure:

- EC2 in private subnet

- WAF for blocking malicious IPs

- CloudFront with HTTPS-only

Data:

- RDS encryption

- Secrets Manager for DB credentials

Detection:

- CloudTrail for auditing

- CloudWatch alarms for CPU, DB connections, errors

Incident Management:

- SNS for critical notifications

- Backup restoration procedures documented

# Activities AND Deliverables

## Activities and deliverables

| Phase | Timeline | Activities | Deliverables | Man-day |
| --- | --- | --- | --- | --- |
| Assessment | Week 1–2 | Requirements, architecture, ERD | Architecture document | 5 |
| Base Infrastructure | Week 3–4 | VPC, subnets, IGW, NAT, EC2, RDS | Network + compute ready | 7 |
| Component Setup 1 | Week 5–6 | API Gateway, Cognito, WAF | API + Auth configured | 5 |
| Component Setup 2 | Week 7–8 | S3 + CloudFront, Route 53 | Frontend deployed | 5 |
| CI/CD & Testing | Week 9–10 | GitLab → CodePipeline → EC2 | Automated pipeline | 6 |
| Go-live | Week 11 | Deployment, monitoring setup | Production release | 3 |
| Handover | Week 12 | KT session, documentation | Ops handbook | 3 |

## OUT OF SCOPE

- AI/ML recommendation engine

- Mobile application development

- Integration with hospital ERP systems

- On-premise data migration

- Multi-region failover setup

## PATH TO PRODUCTION

The PoC includes core functionalities: donor registration, blood search, inventory tracking, and authentication.

To reach production-ready:

- Enhanced error handling

- API rate limiting

- Database optimization for high traffic

- Audit trail dashboards

- Penetration testing

# EXPECTED AWS COST BREAKDOWN BY SERVICES

(Estimated monthly; based on your earlier numbers)

- EC2 (t2.micro) : $3.50

- RDS MySQL : $2.80

- API Gateway : $0.50

- S3 + CloudFront : $0.80

- Route 53 : $0.50

- Cognito : $0.10

- CloudWatch : $0.30

- CI/CD : $0.40

Total: ~$8.9 / month (~$106.8/year)

Assumptions:

- Low traffic <5k requests

- Under AWS Free Tier for S3, CloudFront, Lambda

# TEAM

[Identify and list the customer’s Executive Sponsor and Project Stakeholders, including Title and Description (describe their role and responsibilities in the organization). The Executive Sponsor is the individual with overall accountability for the project. The Sponsor is primarily concerned with ensuring that the project delivers the agreed business benefits.  Project stakeholders are entities that have an interest in a given project, and usually represent a business group or organization]

Partner Executive Sponsor

| Name | Title | Description | Email / Contact Info |
| --- | --- | --- | --- |
| Võ Trường Thành Phát | Executive Sponsor | Responsible for overall project direction and ensuring the project achieves its defined objectives | phatvttse171823@fpt.edu.vn |

John Doe	SVP Finance	 Head of Financial Services

Project Stakeholders

| Name | Title | Stakeholder for | Email / Contact Info |
| --- | --- | --- | --- |
| Nguyễn Kế Thắng | Project Stakeholder | Backend development & technical coordination | nguyenkethang111@gmail.com |
| Phạm Hoàng Hải Nguyên | Team Leader | Front-end, AWS services, cloud architecture | phamhoanghainguyen12a12dt@gmail.com |
| Võ Trường Thành Phát | Project Stakeholder | Backend development, cloud architecture, testing, and quality assurance | phatvttse171823@fpt.edu.vn |
| Đào Nguyên Khôi | Project Stakeholder | Deployment, operations, CI/CD | khoi.dao2411@gmail.com |
| Đỗ Đoàn Duy Phương | Project Stakeholder | Overall project direction, decision-making support | phuongdddse180235@fpt.edu.vn |

Ivan Doctorow	Sr. Manager, QA 	 IT – Testing / QA

Jane Smith	Director, PMO	 Program Management Office

Dan Jacobs	VP, IT Operations	IT Operations – Networking

Partner Project Team

| Name | Title | Role | Email / Contact Info |
| --- | --- | --- | --- |
| Phạm Hoàng Hải Nguyên | Team Leader | Technical Lead, cloud Architect, front-end | phamhoanghainguyen12a12dt@gmail.com |
| Đỗ Đoàn Duy Phương | QA Engineer | Project oversight, strategic direction | phuongdddse180235@fpt.edu.vn |
| Võ Trường Thành Phát | Executive Sponsor | Testing & Quality Assurance, backend Developer | phatvttse171823@fpt.edu.vn |
| Nguyễn Kế Thắng | Developer | Backend Developer, cloud Architect | nguyenkethang111@gmail.com |
| Đào Nguyên Khôi | DevOps Engineer | CI/CD & Deployment Automation | khoi.dao2411@gmail.com |

Steve Jones	Delivery Manager	Project Manager

Philip McDaniels	Sr. Solutions Architect	Architect; Technical Lead

Project Escalation Contacts

| Name | Title | Role | Email / Contact Info |
| --- | --- | --- | --- |
| Phạm Hoàng Hải Nguyên | Team Leader | Escalation Contact | phamhoanghainguyen12a12dt@gmail.com |

Steve Jones	Delivery Manager	Project Manager

# resources & cost estimates

| Resource | Responsibility | Rate (USD) / Hour |
| --- | --- | --- |
| Solution Architects (1 HC) | AWS Architecture Design, Security, VPC, IAM, Monitoring | 0 USD |
| Engineers (4 HC) | Backend (EC2, API Gateway), Database (RDS), Frontend (S3 + CloudFront), CI/CD (GitLab → CodePipeline), Deployment & Operations | 0 USD |
| Other (QA) | Functional, API, Performance Testing | 0 USD |

* Note: Refer to section “activities & deliverables” for the list of project phases

| Project Phase | Solution Architects | Engineers | Other (QA) | Total Hours |
| --- | --- | --- | --- | --- |
| Assessment | 6 | 12 | 4 | 22 |
| Base Infrastructure | 8 | 20 | 2 | 30 |
| Component Setup 1 | 6 | 18 | 2 | 26 |
| Component Setup 2 | 4 | 14 | 2 | 20 |
| CI/CD & Testing | 4 | 16 | 6 | 26 |
| Go-live | 2 | 10 | 4 | 16 |

Cost Contribution distribution between Partner, Customer, AWS:

| Party | Contribution (USD) | % Contribution of Total |
| --- | --- | --- |
| Customer (Student Group) | 0 USD | 0% |
| Partner (Project Team) | 0 USD | 0% |
| AWS | Funded by AWS Credits (1,000 USD) | 100% |

# Additional notes (if needed for explanation)

- Theoretical AWS cost: $8.9/month (~$106.8/year)

- Actual cost the group has to pay: ≈ 0 USD, because:

+ Most services are in the AWS Free Tier
+ Teams are awarded $1,000 in AWS Credits (200×5)

- The system is still operational and can serve real users on a small-medium scale.

# Acceptance

Upon completion of each deliverable, the partner submits deliverables with an Acceptance Form.

Customer has 8 business days to review and approve or reject with detailed feedback.

Rejected items will be fixed and resubmitted.

Lack of response within the acceptance period means auto-acceptance.